{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["Activities","Panduan"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Activities","index":0,"n_rows":29,"n_cols":9,"rows_kept":29,"cut":false,"hidden":false,"merged":[[3,5,3,6],[3,8,4,8],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4]]}
["Form 00: Kegiatan Proyek (Volume Pekerjaan Proyek)"]
["Proyek : "]
["Periode : "]
["Outline Level","Predecessors","No","Task Name","Weight","Plan Date (dd.mm.yyyy)",null,"PIC","Duration (days)"]
[{"$nulls":5},"Start","Finish","NIK"]
[1,null,1,"Surabaya 1",1,"2023-07-18",{"$f":"G29","v":"2023-11-30"},null,{"$f":"NETWORKDAYS(F6,G6)","v":98}]
[2,null,2,"Kampar Siak Hulu 54621",0.05,"2023-07-18",{"$f":"G29","v":"2023-11-30"},null,98]
[3,null,3,"Tahap Survey",5.0000000000000001E-3,{"$f":"F9","v":"2023-07-18"},{"$f":"G10","v":"2023-07-26"},null,{"$f":"NETWORKDAYS(F8,G8)","v":7}]
[4,null,4,"Survey & Tagging",2.5000000000000001E-3,"2023-07-18","2023-07-22",null,{"$f":"NETWORKDAYS(F9,G9)","v":4}]
[4,null,5,"SITAC/PERMIT",2.5000000000000001E-3,"2023-07-23","2023-07-26",null,{"$f":"NETWORKDAYS(F10,G10)","v":3}]
[3,null,6,"Tahap DRM",5.0000000000000001E-3,{"$f":"F12","v":"2023-07-27"},{"$f":"G12","v":"2023-07-29"},null,{"$f":"NETWORKDAYS(F11,G11)","v":2}]
[4,null,7,"DRM",5.0000000000000001E-3,"2023-07-27","2023-07-29",null,2]
[3,null,8,"Tahap Pembangunan",0.01,{"$f":"F14","v":"2023-08-01"},{"$f":"G17","v":"2023-09-25"},null,40]
[4,null,9,"Pembangunan Pondasi+Tiang KWH",2.5000000000000001E-3,"2023-08-01","2023-08-07",null,5]
[4,null,10,"Install Cabinet + Grounding",2.5000000000000001E-3,"2023-08-08","2023-09-04",null,20]
[4,null,11,"PLN Application",2.5000000000000001E-3,"2023-09-05","2023-09-11",null,5]
[4,null,12,"PSB PLN",2.5000000000000001E-3,"2023-09-12","2023-09-25",null,10]
[3,null,13,"Tahap Penarikan",0.01,{"$f":"F19","v":"2023-09-26"},{"$f":"G22","v":"2023-10-20"},null,19]
[4,null,14,"Penarikan Kabel Distribusi",2.5000000000000001E-3,"2023-09-26","2023-10-02",null,5]
[4,null,15,"Penarikan Kabel Uplink",2.5000000000000001E-3,"2023-10-03","2023-10-10",null,{"$f":"NETWORKDAYS(F20,G20)","v":6}]
[4,null,16,"Jointing FAT",2.5000000000000001E-3,"2023-10-11","2023-10-15",null,3]
[4,null,17,"Jointing FDT",2.5000000000000001E-3,"2023-10-16","2023-10-20",null,5]
[3,null,18,"Tahap Integrasi",0.02,{"$f":"F24","v":"2023-10-21"},{"$f":"G29","v":"2023-11-30"},null,29]
[4,null,19,"QC Internal",0.01,{"$f":"F25","v":"2023-10-21"},{"$f":"G26","v":"2023-11-10"},null,15]
[5,null,20,"Pelaksanaan QC Internal",5.0000000000000001E-3,"2023-10-21","2023-10-28",null,5]
[5,null,21,"Rektifikasi",5.0000000000000001E-3,"2023-10-29","2023-11-10",null,{"$f":"NETWORKDAYS(F26,G26)","v":10}]
[4,null,22,"QC dengan ICON",0.01,{"$f":"F28","v":"2023-11-11"},{"$f":"G29","v":"2023-11-30"},null,14]
[5,null,23,"Pelaksanaan QC dengan ICON",5.0000000000000001E-3,"2023-11-11","2023-11-20",null,{"$f":"NETWORKDAYS(F28,G28)","v":6}]
[5,null,24,"Rektifikasi",5.0000000000000001E-3,"2023-11-21","2023-11-30",null,{"$f":"NETWORKDAYS(F29,G29)","v":8}]

{"sheet":"Panduan","index":1,"n_rows":36,"n_cols":6,"rows_kept":36,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,null,"Outline Level","Berguna untuk mengatur aktivitas secara terstruktur dengan cara membagi aktivitas-aktivitas tersebut ke dalam beberapa level hierarkis."]
[null,null,"Predecessor","Berguna untuk menunjukan hubungan urutan dan ketergantungan antar aktivitas dalam proyek."]
[null,null,"No","Berguna sebagai nomor urut aktivitas dan sebagai nilai untuk predecessor"]
[null,null,"Task Name","Berisi nama aktivitas"]
[null,null,"Weight","Berisi bobot pada masing-masing aktivitas"]
[null,null,"Start","Waktu dimulainya aktivitas"]
[null,null,"Finish ","Waktu berakhirnya aktivitas"]
[null,null,"PIC (NIK)","Berisi NIK HR (Human Resource) yang menangani aktivitas"]
[null,null,"Duration","Berisi jumlah durasi hari dalam rentang start dan finish date"]
[]
[]
[null,null,"Contoh :"]
[]
[null,"Outline Level","Task Name","Weight"]
[null,1,"Judul Gantt",1]
[null,2,"Site 1",0.5]
[null,3,"Tahap 1",0.2]
[null,4,"Aktivitas 1",0.1]
[null,4,"Aktivitas 2",0.1,null,"Site 1"]
[null,3,"Tahap 2",0.2]
[null,4,"Aktivitas 1",0.1]
[null,4,"Aktivitas 2",0.1]
[null,3,"Tahap 3",0.1]
[null,2,"Site 2",0.5]
[null,3,"Tahap 1",0.2]
[null,4,"Aktivitas 1",0.1]
[null,4,"Aktivitas 2",0.1]
[null,3,"Tahap 2",0.2,null,"Site 2"]
[null,4,"Aktivitas 1",0.1]
[null,4,"Aktivitas 2",0.1]
[null,3,"Tahap 3",0.1]
[null,4,"Aktivitas 1",0.05]
[null,4,"Aktivitas 2",0.05]