{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Activities"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Activities","index":0,"n_rows":23,"n_cols":10,"rows_kept":23,"cut":false,"hidden":false,"merged":[[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,3,6],[3,7,3,8],[3,9,4,9]]}
["Form 00: Kegiatan Proyek (Volume Pekerjaan Proyek)"]
["Proyek : "]
["Periode : "]
["Outline Level","Predecessors","No","Task Name","Weight","Plan Date (dd.mm.yyyy)",null,"PIC",null,"Duration (days)"]
[{"$nulls":5},"Start","Finish","KITech","Owner"]
[1,null,1,"Implementasi Procurement Information System",1,"2022-07-18",{"$f":"G23","v":"2022-11-27"},null,null,{"$f":"NETWORKDAYS(F6,G6)","v":95}]
[2,null,2,"Project Preparation",{"$f":"J7/J6","v":0.052631578947368418},{"$f":"F8","v":"2022-07-18"},{"$f":"G9","v":"2022-07-24"},null,null,5]
[3,null,3,"Project Charter",0.029999999999999999,"2022-07-18","2022-07-22",null,null,5]
[3,{"$f":"C8","v":3},4,"Sign Off",0.02,"2022-07-22","2022-07-24",null,null,1]
[2,null,6,"Business Blueprint",{"$f":"J10/J6","v":0.052631578947368418},{"$f":"F11","v":"2022-07-25"},{"$f":"G12","v":"2022-07-31"},null,null,{"$f":"NETWORKDAYS(F10,G10)","v":5}]
[3,null,7,"Business Blueprint Document",0.029999999999999999,"2022-07-25","2022-07-29",null,null,5]
[3,{"$f":"C11","v":7},8,"Sign Off",0.02,"2022-07-29","2022-07-31",null,null,1]
[2,null,10,"Realization & development",{"$f":"J13/J6","v":0.42105263157894735},{"$f":"F14","v":"2022-08-01"},{"$f":"G17","v":"2022-09-25"},null,null,40]
[3,{"$f":"C10","v":6},11,"Technical Document",0.10000000000000001,"2022-08-01","2022-08-07",null,null,5]
[3,{"$f":"C14","v":11},12,"Development (Customize)",0.20000000000000001,"2022-08-08","2022-09-04",null,null,20]
[3,12,13,"System Integration Test Document",0.10000000000000001,"2022-09-05","2022-09-11",null,null,5]
[3,13,14,"User Acceptanace Test Document",0.050000000000000003,"2022-09-12","2022-09-25",null,null,10]
[2,null,16,"Cut Over & Data Migration ",{"$f":"J18/J6","v":0.24210526315789474},{"$f":"F19","v":"2022-09-26"},{"$f":"G20","v":"2022-10-26"},null,null,23]
[3,{"$f":"C17","v":14},17,"Cut Over & Data Migration Plan",0.20000000000000001,"2022-09-26","2022-10-02",null,null,5]
[3,{"$f":"C19","v":17},18,"Cut Over & Data Activities ",0.029999999999999999,"2022-10-03","2022-10-26",null,null,18]
[2,null,20,"Go Live & Support",0.22,{"$f":"F22","v":"2022-10-27"},{"$f":"G23","v":"2022-11-27"},null,null,22]
[3,{"$f":"B20","v":17},21,"Go Live",0.20000000000000001,"2022-10-27","2022-10-28",null,null,2]
[3,{"$f":"C22","v":21},22,"Issue Log Document",0.02,"2022-10-28","2022-11-27",null,null,21]