{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["Activities","Panduan"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Activities","index":0,"n_rows":29,"n_cols":7,"rows_kept":29,"cut":false,"hidden":false,"merged":[[3,6,4,6],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4]]}
["Form 00: Kegiatan Proyek (Volume Pekerjaan Proyek)"]
["Proyek : "]
["Periode : "]
["Outline Level","Predecessors","No","Task Name","Weight","PIC","Duration (days)"]
[{"$nulls":5},"NIK"]
[1,null,1,"Surabaya 1",1,null,98]
[2,null,2,"Kampar Siak Hulu 54621",0.05,null,98]
[3,null,3,"Tahap Survey",5.0000000000000001E-3,null,7]
[4,null,4,"Survey & Tagging",2.5000000000000001E-3,null,4]
[4,null,5,"SITAC/PERMIT",2.5000000000000001E-3,null,3]
[3,null,6,"Tahap DRM",5.0000000000000001E-3,null,2]
[4,null,7,"DRM",5.0000000000000001E-3,null,2]
[3,null,8,"Tahap Pembangunan",0.01,null,40]
[4,null,9,"Pembangunan Pondasi+Tiang KWH",2.5000000000000001E-3,null,5]
[4,null,10,"Install Cabinet + Grounding",2.5000000000000001E-3,null,20]
[4,null,11,"PLN Application",2.5000000000000001E-3,null,5]
[4,null,12,"PSB PLN",2.5000000000000001E-3,null,10]
[3,null,13,"Tahap Penarikan",0.01,null,19]
[4,null,14,"Penarikan Kabel Distribusi",2.5000000000000001E-3,null,5]
[4,null,15,"Penarikan Kabel Uplink",2.5000000000000001E-3,null,6]
[4,null,16,"Jointing FAT",2.5000000000000001E-3,null,3]
[4,null,17,"Jointing FDT",2.5000000000000001E-3,null,5]
[3,null,18,"Tahap Integrasi",0.02,null,29]
[4,null,19,"QC Internal",0.01,null,15]
[5,null,20,"Pelaksanaan QC Internal",5.0000000000000001E-3,null,5]
[5,null,21,"Rektifikasi",5.0000000000000001E-3,null,10]
[4,null,22,"QC dengan ICON",0.01,null,14]
[5,null,23,"Pelaksanaan QC dengan ICON",5.0000000000000001E-3,null,6]
[5,null,24,"Rektifikasi",5.0000000000000001E-3,null,8]

{"sheet":"Panduan","index":1,"n_rows":36,"n_cols":6,"rows_kept":36,"cut":false,"hidden":false,"merged":[]}
[]
[]
[]
[null,null,"Outline Level","Berguna untuk mengatur aktivitas secara terstruktur dengan cara membagi aktivitas-aktivitas tersebut ke dalam beberapa level hierarkis."]
[null,null,"Predecessor","Berguna untuk menunjukan hubungan urutan dan ketergantungan antar aktivitas dalam proyek."]
[null,null,"No","Berguna sebagai nomor urut aktivitas dan sebagai nilai untuk predecessor"]
[null,null,"Task Name","Berisi nama aktivitas"]
[null,null,"Weight","Berisi bobot pada masing-masing aktivitas"]
[null,null,"Start","Waktu dimulainya aktivitas"]
[null,null,"Finish ","Waktu berakhirnya aktivitas"]
[null,null,"PIC (NIK)","Berisi NIK HR (Human Resource) yang menangani aktivitas"]
[null,null,"Duration","Berisi jumlah durasi hari dalam rentang start dan finish date"]
[]
[]
[null,null,"Contoh :"]
[]
[null,"Outline Level","Task Name","Weight"]
[null,1,"Judul Gantt",1]
[null,2,"Site 1",0.5]
[null,3,"Tahap 1",0.2]
[null,4,"Aktivitas 1",0.1]
[null,4,"Aktivitas 2",0.1,null,"Site 1"]
[null,3,"Tahap 2",0.2]
[null,4,"Aktivitas 1",0.1]
[null,4,"Aktivitas 2",0.1]
[null,3,"Tahap 3",0.1]
[null,2,"Site 2",0.5]
[null,3,"Tahap 1",0.2]
[null,4,"Aktivitas 1",0.1]
[null,4,"Aktivitas 2",0.1]
[null,3,"Tahap 2",0.2,null,"Site 2"]
[null,4,"Aktivitas 1",0.1]
[null,4,"Aktivitas 2",0.1]
[null,3,"Tahap 3",0.1]
[null,4,"Aktivitas 1",0.05]
[null,4,"Aktivitas 2",0.05]